## Log in
Project Name |  | Dekhi Bangladesh | Environment
Tester's Name |  | Syeda Tanjina Hasan | Reviewed By
Date Tested |  | 2024-01-07 | Version
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment
TS01 | Login | 1.Valid Email Id with Valid Password. 2. Valid Email Id with Invalid Password. 3.Invalid Email Id & Valid Password. 4.Invalid Email Id & Invalid Password. | Logging with Valid Email Id with Valid Password | 1. go to loging website 2. insert user id 3. insert password. 4. click login button. | Bug | High | High | There is no proper reg or logIn system. | Fail | https://drive.google.com/file/d/1IM6xtwfW87_bUymK_YbexM3FZ227vV4d/view?usp=sharing
TS02 | Comment | Click the comment button | Comment button should leads to comment section | 1. go to loging website 2. insert user id 3. insert password. 4. click login button. 5. go to comment section. | Improvement | High | High | clicking the comment button no response from website. | Fail | https://drive.google.com/file/d/1T1yhVvqjBdE1OQey5PKUihTfV4nXoHHh/view?usp=sharing

## Jante Chai
Project Name |  | Dekhi Bangladesh | Environment
Tester's Name |  | Syeda Tanjina Hasan | Reviewed By
Date Tested |  | 2024-01-07 | Version
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment
1 | Jante Chai | Can access with valid name | Logging with Valid first/last Name | 1. go to loging website 2. insert user name 3. insert Email. 4. insert Phone Number. 5. insert কি জানতে চান 6. Click Submit | Improvement | High | High | taking invalid name | Fail | https://drive.google.com/file/d/1Df0TNBUAGOCzEPEAlWZ6cOn4yv4KWoqB/view?usp=sharing

## Bhromon Event
Project Name |  | Dekhi Bangladesh | Environment
Tester's Name |  | Syeda Tanjina Hasan | Reviewed By
Date Tested |  | 2024-01-07 | Version
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment
1 | Bhromon Event | Click and Respose | By clicking each event leads to that section | 1. go to loging website 2. insert user id 3. insert password 4.click to Bhromon Event. 5. click bondha garden. | Improvement | High | High | shouldn't open bondha garden event. | Fail | https://drive.google.com/file/d/18fLwL6laEhyKRcBrnaqImal3B5rc8YKH/view?usp=sharing
2 | Bhromon Event | Click and Respose | By clicking each event leads to that section | 1. go to loging website 2. insert user id 3. insert password 4.click to Bhromon Event. 5. click Ahsanmonjil | Bug | High | High | shouldn't open Ahsan monzil event | Fail | https://drive.google.com/file/d/1WVu0E6enkaX0YD1_gjEex4Lkmley_KRz/view?usp=sharing
3 | Bhromon Event | Click and Respose | By clicking each event leads to that section | 1. go to loging website 2. insert user id 3. insert password 4.click to Bhromon Event. 5. click Ahsanmonjil 6. click anyone option from the right side. | Improvement | High | High | shouldn't take us to boldha garden event | Fail | https://drive.google.com/file/d/1Un7K7GfnkC0cfBsVbC2P9HgDnIZYAS-m/view?usp=sharing

## Feature
Project Name |  | Dekhi Bangladesh | Environment
Tester's Name |  | Syeda Tanjina Hasan | Reviewed By
Date Tested |  | 2024-01-07 | Version
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment
1 | Feature | Valid feature page | Valid feature module have feature option | 1. go to loging website 2. insert user id 3. insert password 4. click into the feature module. | Bug | High | Low | Same as Bhromon event.which is redundancy. | Fail | https://drive.google.com/file/d/1zDy_QzQaZ3yIo8HHrHVpI6rt5tHwIOh4/view?usp=sharing

## Bhromon Obhiggota
Project Name |  | Dekhi Bangladesh | Environment
Tester's Name |  | Syeda Tanjina Hasan | Reviewed By
Date Tested |  | 2024-01-07 | Version
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment
1 | Bhromon Obhiggota | Valid title with Valid Image extentions. | Valid title and description with alid Image extentions | 1. go to loging website 2. insert user id 3. insert password 4. go to bhromon obhiggota. 5. give proper title with description also the right image extentions. | Improvement | High | High | had taken all types of extentions in image section. | Fail | https://drive.google.com/file/d/1CRk1hk3wvREE1FWveHlOfGUZO2dmt0JH/view?usp=sharing
2 | Bhromon Obhiggota | Valid title with Valid Image extentions. | Valid title and description with alid Image extentions | 1. go to loging website 2. insert user id 3. insert password 4. go to bhromon obhiggota. 5. give proper title with description also the right image extentions. | Improvement | High | High | No pop up alart for wrong credentials. | Fail | https://drive.google.com/file/d/1CRk1hk3wvREE1FWveHlOfGUZO2dmt0JH/view?usp=sharing

## Hotel Resort
Project Name |  | Dekhi Bangladesh | Environment
Tester's Name |  | Syeda Tanjina Hasan | Reviewed By
Date Tested |  | 2024-01-07 | Version
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment
1 | Hotel Resort | Proper Hotel and Resort information | Proper Hotel Sections and Resort Section with valid information | 1. go to loging website 2. insert user id 3. insert password 4. go to the hotel and resort module. 5. select dhaka zilla-1. | Bug | High | High | Same as Bhromon Event module. | Fail | https://drive.google.com/file/d/1do-fiNP3T8-1M9KhVxxun6u9FedJViQ5/view?usp=sharing
2 | Hotel Resort | Drop down menu | Drop down menu has sections with right information. | 1. go to loging website 2. insert user id 3. insert password 4. go to the hotel and resort module. 5. select dhaka zilla-1. | Bug | High | High | All 3 dropdown option has same information like Bhromon Event module. | Fail | https://drive.google.com/file/d/1do-fiNP3T8-1M9KhVxxun6u9FedJViQ5/view?usp=sharing

## Zilla
Project Name |  | Dekhi Bangladesh | Environment
Tester's Name |  | Syeda Tanjina Hasan | Reviewed By
Date Tested |  | 2024-01-07 | Version
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment
1 | Zilla | Valid Place with right place to visit | Valid Place in each zilla with right place of information to visit | 1. go to loging website 2. insert user id 3. insert password 4. go to Zilla module. 5. select any zilla. | Improvement | High | High | As Expected | Loging Successful | https://drive.google.com/file/d/1R3i1MZIBnr23U05sSC7MuWKkXMdKGzo9/view?usp=sharing